## Seaweed value Chain
Intermediate | Women‑led, climate‑resilient seaweed value chains are strengthened and integrated into inclusive blue economy markets in coastal Kenya
Immediate 1 | Climate‑resilient and reliable seaweed supply systems are established for women producers
Outputs 1 | Sustainable, accessible and reliable seaweed seed systems are established and governed | Climate‑smart seaweed production practices are adopted by women producers | Quality assurance and traceability systems are operational at production level
Activities 1 | Establish floating and/or land‑based seaweed nurseries in priority sites | Introduce and pilot climate‑resilient cultivation methods (e.g. long‑line systems, depth adjustment) | Develop and roll out farm‑level quality standards (drying, moisture, contamination)
| Develop seed multiplication, rotation, and biosecurity protocols | Develop and disseminate seasonal SOPs (heat stress, strong currents, disease response) | Train producer groups on grading, post‑harvest handling, and storage
| Train women and youth as nursery operators and seed custodians | Provide targeted inputs (ropes, lines, drying racks, safety equipment) | Pilot simple traceability systems (batching, records, digital tools where feasible)
| Establish community‑level seed governance agreements (access, replenishment, quality control | Deliver hands‑on training and coaching for women producers | Establish internal inspection and peer‑monitoring mechanisms within groups/cooperative
| Create a simple seed governance system (who maintains, who accesses, replenishment rules, contamination protocols | Minimum quality standards (moisture, cleanliness, drying uniformity) and lot traceability | Establish grading standards and training (moisture content, impurities, drying)
Improve drying infrastructure (raised racks, rain protection, storage)
Deep water
Immediate 2 | Women‑led seaweed enterprises are strengthened and upgraded across the value chain
Outputs 2 | Women‑led producer organizations and SMEs are formalized and operationally strengthened | Value addition and processing capacity for seaweed products is enhanced | Local seaweed‑related service enterprises are established or strengthened
Activities 2 | Map and assess women‑led seaweed producer groups and MSMEs | Identify viable value‑addition pathways (drying, grading, basic processing, product development) | Support development of service SMEs (nurseries, logistics, drying, transport, maintenance)
| Support formalization (registration, governance structures, bylaws) | Provide technical assistance on processing methods, QA/QC, and compliance | Provide technical and business coaching to service providers
| Deliver business management training (costing, records, planning) | Pilot small‑scale processing and value‑addition infrastructure | Facilitate contractual relationships between service SMEs and producer groups
| Strengthen gender‑equitable governance and leadership within enterprises | Support product development trials (e.g. food, cosmetics, biostimulants where feasible) | Promote youth and women’s participation in service‑based roles
| choose 3 enterprise archetypes: | Biostimulant
| Run a structured needs assessment: governance, working capital, equipment, compliance, market readiness | Research
Segment enterprises into: ready now, needs incubation, not viable yet
| “Climate-smart operations” and environmental compliance training | Aggregation Centres
Immediate 3 | Women‑led seaweed enterprises access markets, finance, and enabling services
Outputs 3 | Market access and commercial relationships for seaweed enterprises are strengthened | Inclusive financial products and blended‑finance mechanisms for seaweed SMEs are developed and piloted | Business development and sector support services respond to the needs of women‑led seaweed enterprises
Activities 3 | Identify and engage domestic and international buyers and processors | Conduct financial readiness assessments for women‑led SMEs | Strengthen capacity of local BDS providers to serve seaweed SMEs
| Facilitate buyer–seller matchmaking and negotiation support | Develop SME investment profiles and pitch materials | Facilitate partnerships between enterprises and extension, finance, and logistics services
| Support development of offtake agreements and trial purchase contracts | Design and pilot blended‑finance instruments (e.g. matching grants, guarantees, PO finance) | Support coordination platforms linking SMEs, buyers, financiers, and regulators
| Pilot branding, packaging, and market information tools where appropriate | Engage financial institutions and impact investors to test seaweed‑specific products | Promote gender‑responsive service delivery models
| Buyer-seller events + trade fairs; negotiation coachin | Mobilize county or national grants
| Explore mobile trade apps/market info systems | Design risk-sharing tools: purchase ordLead firm / pull-effect approacher finance, guarantee mechanisms, matching grants | Shared Services Hub functions
Note on D27: My recommendation: Keep the stream seaweed-first, but include one “adjacent enterprise basket” that complements seaweed and reduces risk: Seaweed-adjacent services/products: drying services, transport, equipment repair, packaging, nursery services One additional NbS enterprise track (e.g., eco-tourism, crab, beekeeping) only if it’s clearly linked to ecosystem stewardship and women’s enterprise development (your design notes list these as possibilities).
Note on C34: Archetype 1: Producer coops / clusters: Primary role: aggregation, QA/QC enforcement, traceability, negotiating sales Archetype 2: Service SMEs: Seed supply, farm services, transport/logistics, drying services, equipment maintenance (often youth-led) Archetype 3: Value-add SMEs: Basic processing, cosmetics/soap makers, food products, biostimulant production,
Note on D34: Establish “biostimulant working group” (research + SMEs + agriculture partners) Run greenhouse/on-farm trials with clear protocols and comparison groups Develop local production SOPs for simple biostimulant formulations (if feasible and compliant)
Note on D56: Identify 1–2 anchor buyers/processors early Co-design product specs and delivery cadence Use pilots (trial orders) before large-scale expansion Negotiate fair contracting clauses to protect women producers (timely payment, dispute resolution)
Note on E56: Quality lab / moisture testing kits (portable) Input procurement and distribution Traceability support + data entry Business coaching clinic days Buyer engagement and logistics coordination

## Restoration
MANGROVE RESTORATION AND CONSERVATION
CONSERVATION | 2. RESTORATION | COMMUNITY/INSTITUTIONAL GOVERNANCE
Community Forest monitors | Restoration Plans
KFS taking action | 2.1 HYDRO RESTORATION
Technology | 2.1 PLANTING
Physical posts | Nursery (via user Groups)
Fencing | Enrichment et all
Sensitizing | Follow conservation plan
Community by-law system | Monitoring
CFA / User Group | Planting groups and plans (user groups)
More power to community scouts
Economic Incentive for protection - market oriented livelihoods - crab/bee/tourism
VMU - fish as livelihoods
Full economic intervention - market systems not just IGA
CFA / User Group strenthen
Carbon Project developer | Feasability study
Prepare documentation (carbon stock assessment)
Register with registry (e.g. VERA)
Implementation
Verification and validation
Agreement with KG and KFS - authorization
Preparedness (community) to receive that 40%

## Sheet2
Module D — Care-aware, inclusive participation package: Women’s participation is care-aware and safe (workable scheduling, childcare during peaks, mobility/boat skills addressed)