## Mangrove
COSME Project - Mangrove
Output & Activity Data
Reporting Period: SAR Y3
Last Update: November 2025
Output 1112: Members of mangrove groups trained and coached in mangrove restoration and conservation
REGISTRATION
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved | Notes
Number of Groups | 39 |  |  | 42 |  |  | 40 |  |  | 2 | 105% | 4 groups dropped ou before training, 3 new groups were registered
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Registered | 854 | 297 | 1151 | 973 | 371 | 1344 | 840 | 360 | 1200 | 193 | 112%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
Number of Modules Imparted | 2 |  |  | 4 |  |  | 5 |  |  | 5 | 80%
TRAINING (STRICT THRESHOLD)
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Trained (3 and above) | 0 | 0 | 0 | 640 | 27 | 667 | 840 | 360 | 1200 | 667 | 55.58%
| Y2 |  |  | Y3 (SA) |  |  | Overall Registered |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Trained (3 modules and above) | 0 | 0 | 0 | 640 | 27 | 667 | 973 | 371 | 1344 | 667 | 49.63%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Kilifi | Kwale | All | Kilifi | Kwale | All | Kilifi | Kwale | All
Members Trained (3 and above) | 0 | 0 | 0 | 313 | 354 | 667 | 725 | 476 | 1201 | 667 | 55.54%
TRAINING (SOFT THRESHOLD) | [12 empty] | Add soft Threshold analysis
Participants completing Mangrove Training by module (All)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 1200 | 1344 | 899 | 74.92% | 66.89%
Module 2 | 1200 | 1344 | 791 | 65.92% | 58.85%
Module 3 | 1200 | 1344 | 798 | 66.5% | 59.38%
Module 4 | 1200 | 1344 | 881 | 73.42% | 65.55%
Module 5 | 1200 | 1344 | 816 | 68% | 60.71%
Grand Total | 1200 | 1344 | 842.25 | 70.19% | 62.67%
Participants completeing Mangrove Training by module (Male)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 360 | 371 | 216 | 60% | 58.22%
Module 2 | 360 | 371 | 195 | 54.17% | 52.56%
Module 3 | 360 | 371 | 166 | 46.11% | 44.74%
Module 4 | 360 | 371 | 198 | 55% | 53.37%
Module 5 | 360 | 371 | 177 | 49.17% | 47.71%
Grand Total | 360 | 371 | 193.75 | 53.82% | 52.22%
Participants completeing Mangrove Training by module (Female)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 840 | 973 | 683 | 81.31% | 70.2%
Module 2 | 840 | 973 | 596 | 70.95% | 61.25%
Module 3 | 840 | 973 | 632 | 75.24% | 64.95%
Module 4 | 840 | 973 | 683 | 81.31% | 70.2%
Module 5 | 840 | 973 | 639 | 76.07% | 65.67%
Grand Total | 840 | 973 | 648.5 | 77.2% | 66.65%
COSME Project - Mangrove
Output & Activity Data
Reporting Period: AR Y3
Last Update:

## Seaweed
COSME Project - Seaweed
Output & Activity Data
Reporting Period: SAR Y3
Last Update: November 2025
Output 1122: Women-led seaweed groups trained in seaweed production, value addition and commercialization
REGISTRATION
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved | Notes
Number of Groups | 20 |  |  | 19 |  |  | 20 |  |  | -1 | 95% | 2 groups merged into one group hence reduction from 20 y2 to 19 y3
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Registered | 578 | 170 | 748 | 651 | 191 | 842 | 600 | 0 | 600 | 94 | 140.3%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
Number of Modules Imparted | 2 |  |  | 3 |  |  | 5 |  |  | 5 | 60%
TRAINING (STRICT THRESHOLD)
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Trained (3 and above) | 0 | 0 | 0 | 640 | 27 | 667 | 840 | 360 | 1200 | 667 | 55.58%
| Y2 |  |  | Y3 (SA) |  |  | Overall Registered |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Trained (3 modules and above) | 0 | 0 | 0 | 640 | 27 | 667 | 651 | 191 | 842 | 667 | 79.22%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Kilifi | Kwale | All | Kilifi | Kwale | All | Kilifi | Kwale | All
Members Trained (3 and above) | 0 | 0 | 0 | 313 | 354 | 667 | 725 | 476 | 1201 | 667 | 55.54%
TRAINING (SOFT THRESHOLD) | [12 empty] | Add soft Threshold analysis
Participants completing Seaweed Training by module (All)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 600 | 842 | 314 | 52.33% | 37.29%
Module 2 | 600 | 842 | 375 | 62.5% | 44.54%
Module 3 | 600 | 842 | 603 | 100.5% | 71.62%
Module 4 | 600 | 842 | 508 | 84.67% | 60.33%
Module 5 | 600 | 842 | 512 | 85.33% | 60.81%
Grand Total | 600 | 842 | 462.4 | 77.07% | 54.92%
Participants completeing Seaweed Training by module (Male)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 0 | 371 | 0 | #DIV/0! | 0%
Module 2 | 0 | 371 | 0 | #DIV/0! | 0%
Module 3 | 0 | 371 | 0 | #DIV/0! | 0%
Module 4 | 0 | 371 | 0 | #DIV/0! | 0%
Module 5 | 0 | 371 | 0 | #DIV/0! | 0%
Grand Total | 0 | 371 | 0 | #DIV/0! | 0%
Participants completeing Seaweed Training by module (Female)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 600 | 651 | 314 | 52.33% | 48.23%
Module 2 | 600 | 651 | 375 | 62.5% | 57.6%
Module 3 | 600 | 651 | 603 | 100.5% | 92.63%
Module 4 | 600 | 651 | 508 | 84.67% | 78.03%
Module 5 | 600 | 651 | 512 | 85.33% | 78.65%
Grand Total | 600 | 651 | 462.4 | 77.07% | 71.03%
COSME Project - Mangrove
Output & Activity Data
Reporting Period: AR Y3
Last Update:

## Forest
COSME Project -Forestry
Output & Activity Data
Reporting Period: SAR Y3
Last Update: November 2025
Output 1131: Targeted local communities, especially women, trained in gender-responsive forest management and community-centred conservation
REGISTRATION
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved | Notes
Number of Groups | 52 |  |  | 52 |  |  | 45 |  |  | 0 | 115.6%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Registered | 1303 | 340 | 1643 | 1141 | 299 | 1440 | 945 | 405 | 1350 | -203 | 106.7%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
Number of Modules Imparted | 5 |  |  | 7 |  |  | 7 |  |  | 2 | 100%
TRAINING (STRICT THRESHOLD)
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Trained (5m and above) | ND | ND | ND | 461 | 89 | 550 | 945 | 405 | 1350 | ND | 40.74%
| Y2 |  |  | Y3 (SA) |  |  | Overall Registered |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Trained (5m and above) | N/A | N/A | N/A | 461 | 89 | 550 | 1141 | 299 | 1440 | #VALUE! | 38.19%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Kilifi | Kwale | All | Kilifi | Kwale | All | Kilifi | Kwale | All
Members Trained (5m and above) | ND | ND | ND | 366 | 184 | 550 | 594 | 756 | 1350 | ND | 40.74%
TRAINING (SOFT THRESHOLD)
Participants completing Forestry Training by module (All) - Y3 (SA)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 1350 | 1440 | 1059 | 78.44% | 73.54%
Module 2 | 1350 | 1440 | 947 | 70.15% | 65.76%
Module 3 | 1350 | 1440 | 954 | 70.67% | 66.25%
Module 4 | 1350 | 1440 | 1068 | 79.11% | 74.17%
Module 5 | 1350 | 1440 | 1150 | 85.19% | 79.86%
Module 6 | 1350 | 1440 | 986 | 73.04% | 68.47%
Module 7 | 1350 | 1440 | 1047 | 77.56% | 72.71%
Grand Total | 1350 | 1440 | 1030.1429 | 76.31% | 71.54%
Reference - Y2 | 1350 | 1440 | 1024 | 75.85% | 71.11%
Participants completeing Forestry Training by module (Male) - Y3 (SA)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 405 | 299 | 200 | 49.38% | 66.89%
Module 2 | 405 | 299 | 164 | 40.49% | 54.85%
Module 3 | 405 | 299 | 167 | 41.23% | 55.85%
Module 4 | 405 | 299 | 229 | 56.54% | 76.59%
Module 5 | 405 | 299 | 219 | 54.07% | 73.24%
Module 6 | 405 | 299 | 188 | 46.42% | 62.88%
Module 7 | 405 | 299 | 217 | 53.58% | 72.58%
Grand Total | 405 | 299 | 197.7143 | 48.82% | 66.13%
Reference - Y2 | 405 | 299 | 190 | 46.91% | 63.55%
Participants completeing Forestry Training by module (Female) - Y3 (SA)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 945 | 1141 | 859 | 90.9% | 75.28%
Module 2 | 945 | 1141 | 783 | 82.86% | 68.62%
Module 3 | 945 | 1141 | 787 | 83.28% | 68.97%
Module 4 | 945 | 1141 | 839 | 88.78% | 73.53%
Module 5 | 945 | 1141 | 931 | 98.52% | 81.6%
Module 6 | 945 | 1141 | 798 | 84.44% | 69.94%
Module 7 | 945 | 1141 | 830 | 87.83% | 72.74%
Grand Total | 945 | 1141 | 832.4286 | 88.09% | 72.96%
Reference - Y2 | 945 | 1141 | 834 | 88.25% | 73.09%
ND: No data available
Narrative Summary
Insights
Recommendations

## GJJ
COSME Project - GJJ
Output & Activity Data
Reporting Period: SAR Y3
Last Update: November 2025
Output 1211: Targeted women trained on gender responsive NbS, economic rights, life skills, & GE&I, including UPCW
REGISTRATION
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved | Notes
Number of Groups | 111 |  |  | 113 |  |  | 110 |  |  | 2 | 102.7% | Terrestrial and Mangrove surpassed project target groups
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
| Female | Male | All | Female | Male | All | Female | Male | All
Members Registered | 2735 | 807 | 3542 | 2765 | 861 | 3626 | 3000 | 0 | 3000 | 84 | 120.9%
| Y2 |  |  | Y3 (SA) |  |  | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
Number of Modules Imparted | 3 |  |  | 2 |  |  | 6 |  |  | -1 | 83.33%
TRAINING (STRICT THRESHOLD)
[7 empty] | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
[7 empty] | Female | Male | All
Members Trained (3 and above) | [6 empty] | 840 | 360 | 1200 | 0 | 0%
[7 empty] | Overall Registered |  |  | Y3 (SA) - Y2 | % Achieved
[7 empty] | Female | Male | All
Members Trained (3 modules and above) | [6 empty] | 2765 | 861 | 3626 | 0 | 0%
[7 empty] | Overall Target |  |  | Y3 (SA) - Y2 | % Achieved
[7 empty] | Kilifi | Kwale | All
Members Trained (3 and above) | [6 empty] | 725 | 476 | 1201 | 0 | 0%
TRAINING (SOFT THRESHOLD) | [12 empty] | Add soft Threshold analysis
Participants completing GJJ Training by module (All)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 3000 | 3626 | 2072 | 69.07% | 57.14%
Module 2 | 3000 | 3626 | 1843 | 61.43% | 50.83%
Module 3 | 3000 | 3626 | 2246 | 74.87% | 61.94%
Module 4 | 3000 | 3626 | 2328 | 77.6% | 64.2%
Module 5 | 3000 | 3626 | 2083 | 69.43% | 57.45%
Grand Total | 3000 | 3626 | 2114.4 | 70.48% | 58.31%
Participants completeing GJJ Training by module (Male)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 0 | 861 | 0 | #DIV/0! | 0%
Module 2 | 0 | 861 | 0 | #DIV/0! | 0%
Module 3 | 0 | 861 | 0 | #DIV/0! | 0%
Module 4 | 0 | 861 | 0 | #DIV/0! | 0%
Module 5 | 0 | 861 | 0 | #DIV/0! | 0%
Grand Total | 0 | 861 | 0 | #DIV/0! | 0%
Participants completeing GJJ Training by module (Female)
Modules | All
| Target | Registered | Completed | Target(%) | Reg(%)
Module 1 | 3000 | 2765 | 2072 | 69.07% | 74.94%
Module 2 | 3000 | 2765 | 1843 | 61.43% | 66.65%
Module 3 | 3000 | 2765 | 2246 | 74.87% | 81.23%
Module 4 | 3000 | 2765 | 2328 | 77.6% | 84.2%
Module 5 | 3000 | 2765 | 2083 | 69.43% | 75.33%
Grand Total | 3000 | 2765 | 2114.4 | 70.48% | 76.47%