Revised Life of Project Gantt Chart

|  |  | Q1 | Q1 | Q1 |
| --- | --- | --- | --- | --- |
| Intermediate Outcome | 1100 Enhanced adoption of gender-responsive and socially inclusive nature- based solutions (NbS) for climate change adaptation with biodiversity and ecosystem integrity co-benefits | Week1 | Week2 | Week3 |
| Immediate Outcome | 1110 Increased capacity of communities, especially women, to undertake gender-responsive and equitable mangrove restoration and conservation with biodiversity co-benefits |  |  |  |
| Output | 1111 Biodiversity assessment for mangrove restoration conducted |  |  |  |
| Activity | 1111.1 Map mangrove and other coastal forest ecosystems (current and potential) | X |  |  |
| Activity | 1111.2 Conduct biodiversity assessment on mangroves ecosystems in target communities | X |  |  |
| Output | 1112 Members of mangrove groups trained and coached in mangrove restoration, conservation |  |  |  |
| Activity | 1112.1 Identify mangrove groups (current and potential) to be trained in mangrove management, conservation | X |  |  |
| Activity | 1112.2 Conduct TNA (technical needs assessment) and opportunities on mangrove restoration, conservation and technical and capacity needs of mangrove groups | X |  |  |
| Activity | 1112.3 Develop/tailor content for training on mangrove restoration, conservation | X |  |  |
| Activity | 1112.4 Provide ToT on mangrove restoration, conservation | X |  |  |
| Activity | 1112.5 Train mangrove groups on restoration and conservation | X |  | X refresher |
| Activity | 1112.6 Provide follow-up and ongoing mentorship support | X | X | X |
| Output | 1113 Mangrove groups equipped with restoration and conservation inputs |  |  |  |
| Activity | 1113.1 Support mangrove groups to become formally registered Beach Management Units and Community Forest Associations | X |  |  |
| Activity | 1113.2 Provide inputs for mangrove restoration and conservation to mangrove groups | X | X |  |
| Immediate Outcome | 1120 Increased capacity of women-led cooperatives to undertake regenerative and sustainable seaweed production, value addition and commercialization |  |  |  |
| Output | 1121 Gendered market and environmental assessment, and research into improved seaweed varietals conducted |  |  |  |
| Activity | 1121.1 Review cultural and environmental context for local seaweed cultivation and farm site suitability | X |  |  |
| Activity | 1121.2 Undertake research and development into the most locally relevant climate- resilient seaweed varietals and biobank | X |  |  |
| Activity | 1121.3 Undertake gendered local and export market analysis (current and new markets) and value addition opportunities (soap, detergent, biostimulant, food, livestock feed) | X | X |  |
| Activity | 1121.4 Develop and distribute one-year outlook tide table | X | X | X |
| Output | 1122 Women-led seaweed groups trained in seaweed production, value addition and commercialization |  |  |  |
| Activity | 1122.1 Identify women-led seaweed groups | X |  |  |
| Activity | 1122.2 Develop and adapt training materials on seaweed production, value addition and commercialization (business plans, finance management, links to financial services, local grants, etc.) | X |  |  |
| Activity | 1122.3 Conduct ToT on seaweed production, value addition and commercialization | X |  |  |
| Activity | 1122.4 Conduct training for women-led groups on seaweed production, value addition and commercialization | X | X | X refresher |
| Activity | 1122.5 Provide follow-up and ongoing mentorship support | X | X | X |
| Output | 1123 Women-led seaweed groups provided with inputs to sustain or improve seaweed production |  |  |  |
| Activity | 1123.1 Undertake needs assessment of equipment and supplies for existing seaweed groups | X |  |  |
| Activity | 1123.2 Provide inputs to women-led seaweed groups to sustain or improve seaweed production | X | X |  |
| Activity | 1123.3 Develop nursery to support biobank and seaweed groups | X | X |  |
| Activity | 1123.4 Develop sustainable mechanism for groups' access to biobank | X | X |  |
| Output | 1124 High-capacity women-led seaweed groups supported through innovation pilots for crop resilience, yield improvement, or value-addition |  |  |  |
| Activity | 1124.1 Identify women-led seaweed groups with capacity to participate in innovation Pilots | X | X |  |
| Activity | 1124.2 Develop innovations for crop resilience, yield improvement, or value-addition and establish methods for piloting with selected women-led seaweed groups | X |  |  |
| Activity | 1124.3 Implement innovation pilots with selected women-led seaweed groups and provide training in monitoring and maintenance to relevant stakeholders | X | X | X |
| Activity | 1124.4 Document and disseminate lessons learned to women-led groups and relevant stakeholders |  | X | X |
| Immediate Outcome | 1130 Increased capacity of communities, especially women, to undertake gender-responsive, locally-led forest management and conservation |  |  |  |
| Output | 1131 Targeted local communities, especially women, trained in gender-responsive forest management and community-centred conservation |  |  |  |
| Activity | 1131.1 Lead sensitization sessions on gender-focused conservation for local authorities | X |  |  |
| Activity | 1131.2 Develop locally relevant and gender-responsive training content on sustainable forest regeneration, enrichment planting, forest product harvesting, and wildfire management | X |  |  |
| Activity | 1131.3 Conduct locally relevant and gender-sensitive training sessions with forest conservation groups on gender-focused conservation for local authorities and target communities | X |  | X refresher |

|  |  | W1 | W2 | W3 |
| --- | --- | --- | --- | --- |
| Output | 1132 Targeted local women's groups supported to promote and pilot NbS based on forestry, including patrols and governance structures for gender responsive forest management & community-centred conservation |  |  |  |
| Activity | 1132.1 Facilitate gender-responsive actions on sustainable forest regeneration, enrichment planting, and wildfire management to target community groups (at least 60% women) | X | X | X |
| Activity | 1132.2 Promote local community members, especially women, in governance structures and forest management decision-making | X | X | X |
| Activity | 1132.3 Increase community-led forest monitoring and patrols led by local authorities | X | X | X |
| Intermedia te Outcome | 1200 Increased agency of women in their diversity to exercise their right to participate in gender-responsive, nature-based solutions with biodiversity co-benefits to increase adaptive capacity and build household and community resilience |  |  |  |
| Immediate Outcome | 1210 Increased knowledge and skills of women on gender responsive NbS, economic rights, life skills, & GE&I |  |  |  |
| Output | 1211 Targeted women trained on gender responsive NbS, economic rights, life skills, & GE&I, including UPCW |  |  |  |
| Activity | 1211.1 Develop and adapt content for training on climate change, economic rights, life skills, & GE&I | X |  |  |
| Activity | 1211.2 Provide ToT on climate change, economic rights, life skills, & GE&I | X | X refresher |  |
| Activity | 1211.3 Conduct trainings and provide coaching on climate change, economic rights, life skills, & GE&I with women | X | X | X |
| Activity | 1211.4 Facilitate peer to peer learning exchanges among targeted women |  | X | X |
| Activity | 1211.5 Provide post-training support and follow-up support, including referrals (peer support - trained facilitators - referral for cases of GBV etc.) | X | X | X |
| Immediate Outcome | 1220 Increased access to resilience building assets and opportunities for women |  |  |  |
| Output | 1221 Women's savings groups established or strengthened |  |  |  |
| Activity | 1221.1: Map existing SGs and identify communities for new groups | X |  |  |
| Activity | 1221.2: Review and adapt SG materials | X |  |  |
| Activity | 1221.3: Provide supplies to new and existing SGs on a needs basis (box, passbook, stamps) | X |  |  |
| Activity | 1221.4: Train community-based trainers (CBTs) as facilitators on SG methodologies | X |  |  |
| Activity | 1221.5: Roll out SGs and deliver foundational training | X | X |  |
| Activity | 1221.6: Provide regular monitoring and support to SGs | X | X | X refresher |
| Activity | 1221.7 Create linkages with financial institutions to offer credit facilities to women |  | X | X |
| Output | 1222 Women-led demonstration plots on regenerative agriculture supported |  |  |  |
| Activity | 1222.1 Identify shared land for demonstration plots | X | X |  |
| Activity | 1222.2 Develop and adapt training materials on regenerative agriculture | X | X |  |
| Activity | 1222.3 Identify and train facilitators for the training | X | X |  |
| Activity | 1222.4 Deliver training to targeted households on regenerative agriculture | X | X | X refresher |
| Activity | 1222.5 Provide rainwater harvesting and drip-irrigation solutions to demonstration plots | X | X |  |
| Activity | 1122.6 Provide input support such as seeds, nature fertilizer, farm tools for crop production | X | X | X |
| Activity | 1222.7 Undertake post training assessment and provide follow-up and coaching | X | X | X |
| Activity | 1222.8 Hold awareness information dissemination sessions with regenerative agriculture groups on opportunities | X | X | X |
| Output | 1223 Solar and improved technology solutions distributed to targeted women to reduce fuelwood harvesting, improve air quality, and reduce time poverty |  |  |  |
| Activity | 1223.1 Train partners/participants on solar panels, cook stoves and associated kit operation and maintenance |  | X | X |
| Activity | 1223.2 Procure and distribute solar kits and solar panels | X | X |  |
| Activity | 1223.3 Procure and distribute fuel efficient cooking supplies | X | X | X |
| Immediate Outcome | 1230 Increased capacity of community members and leaders, particularly men, to promote and support gender equality, women's rights and engagement in gender-responsive NbS with biodiversity co-benefit |  |  |  |
| Output | 1231 SBCC strategy to promote gender responsive NbS, economic rights & GE&I, including UPCW |  |  |  |
| Activity | 1231.1 Conduct participatory design workshop to inform and design SBCC strategy to address gender responsive NbS, economic rights & GE&I, including UPCW | X |  |  |
| Activity | 1231.2 Develop/adapt content for SBCC material | X |  |  |
| Activity | 1231.3 Print material and produce media for SBCC strategy | X |  |  |
| Activity | 1231.4 Implement SBCC strategy (launch, community fairs, murals, distribution of printed material, radio programs, banners) | X | X | X |
| Output | 1232 Change Agents trained and supported to promote gender responsive NbS, economic rights & GE&I, including UPCW |  |  |  |
| Activity | 1232.1 Map and identify potential Change Agents | X |  |  |
| Activity | 1232.2 Develop/contextualize training material and information aids for Change Agents | X |  |  |
| Activity | 1232.3 Train Change Agents | X |  | X refresher |
| Activity | 1232.4 Support Change Agents to develop community sensitization action plans | X |  |  |
| Activity | 1232.5 Provide Change Agents with technical follow-up and materials for the implementation of their community sensitization action plans | X | X | X |
| Activity | 1232.6 Organize regional experience-sharing and learning exchanges for Change Agents |  | X | X |
| Activity | 1232.7 Organize inter-generational dialogues between YLOs and Change Agents |  | X | X |

|  |  | W1 | W2 | W3 |
| --- | --- | --- | --- | --- |
| Output | 1233 Men trained to promote and support gender responsive NbS, economic rights & GE&I, including UPCW |  |  |  |
| Activity | 1233.1 Engage and recruit training participants as Male Champions | X |  |  |
| Activity | 1233.2 Develop and adapt content for training, including retention strategy, to promote and support gender responsive NbS, economic rights & GE&I, including UPCW | X |  |  |
| Activity | 1233.3 Provide ToT on training content | X |  |  |
| Activity | 1233.4 Conduct trainings and provide coaching on content | X | X | X |
| Activity | 1233.5 Conduct post training coaching and mentoring sessions with trained groups |  | X | X |
| Output | 1234 Inclusive gender-transformative household action plans developed and implemented in support of women's participation in gender responsive NbS (roles and responsibilities, decision making, access and control) |  |  |  |
| Activity | 1234.1 Develop and adapt household action plan methodology and tools | X |  |  |
| Activity | 1234.2 Provide ToT on household action plan methodology and tools | X | X |  |
| Activity | 1234.3 Facilitate the development of household action plans with targeted families |  | X |  |
| Activity | 1234.4 Monitor implementation of household action plans |  | X | X |
| Activity | 1234.5 Facilitate reflection and sharing between targeted households and communities |  | X | X |
| Intermediate Outcome | 1300 Improved gender-responsive and child/youth-friendly governance for climate adaptation, resilience and biodiversity |  |  |  |
| Immediate Outcome | 1310 Increased awareness and knowledge of primary school children, particularly girls, on climate change, NbS, and conservation |  |  |  |
| Output | 1311 4K and Roots and Shoots clubs established and trained on climate change, and conservation |  |  |  |
| Activity | 1311.1 Conduct project sensitization to Ministry of Education, Teachers Service Commission (TSC) and schools to generate buy-in and sign agreements | Completed |  |  |
| Activity | 1311.2 Map existing 4K and Roots and Shoots school clubs | Completed |  |  |
| Activity | 1311.3 Establish new 4K and Roots and Shoots clubs where not existing | X |  |  |
| Activity | 1311.4 Revise and contextualize training program material and methodology (4K Club, Climate Cards and Roots & Shoots) | X |  |  |
| Activity | 1311.5 Train facilitators on program methodology and CP (school teachers, SMC members, BoM, Community Champions) | X |  |  |
| Activity | 1311.6 Implement training program with groups | X | X | X refresher |
| Activity | 1311.7 Provide coaching, mentoring and supportive supervision to facilitators and BOMs | X | X | X |
| Output | 1312 4K and Roots and Shoots clubs supported to implement community based climate change, and conservation initiatives |  |  |  |
| Activity | 1312.1 Support the development of community based climate change, and conservation initiatives by 4K and Roots and Shoots clubs | X | X |  |
| Activity | 1312.2 Provide material support for implementation for 4k and Roots and Shoots clubs (inputs and technical assistance) | X | X |  |
| Activity | 1312.3 Facilitate learning and sharing exchanges between 4K and Roots and Shoots clubs |  | X | X |
| Output | 1313 Innovative clean water solution established in targeted schools |  |  |  |
| Activity | 1313.1 Form and build capacity of school-based water management and maintenance clubs | X | X |  |
| Activity | 1313.2 Provide Solvatten kits in targeted schools | X |  |  |
| Activity | 1313.3 Establish demonstration plots for drip-irrigation at target schools including management and maintenance committees | X | X | X |
| Activity | 1313.4 Provide rainwater harvesting and drip-irrigation solutions to targeted schools |  | X |  |
| Immediate Outcome | 1320 Strengthened gender responsive community governance structures to reduce risk and enhance preparedness to climate change |  |  |  |
| Output | 1321 Community-level gender responsive adaptation and preparedness plans developed and funded |  |  |  |
| Activity | 1321.1 Develop and adapt participatory risk assessment and planning tools and methodology |  | X |  |
| Activity | 1321.2 Train facilitators on participatory risk assessment and planning tools and methodology |  | X |  |
| Activity | 1321.3 Conduct participatory multi-hazard risk assessment in targeted communities |  | X |  |
| Activity | 1321.4 Analyze and summarize findings from multi-hazard risk assessment |  | X |  |
| Activity | 1321.5 Facilitate evidence based participatory planning with community stakeholders to develop gender responsive adaptation and preparedness plans |  | X | X |
| Activity | 1321.6 Provide material support for selected initiatives in community gender responsive adaptation and preparedness plans |  | X | X |
| Activity | 1321.7 Provide ongoing supportive supervision to the implementation of gender responsive adaptation and preparedness plans |  | X | X |
| Output | 1322 Communities linked with county level and national climate, risk reduction and preparedness funds |  |  |  |
| Activity | 1322.1 Map existing national and county climate, risk reduction and preparedness funding mechanisms and opportunities |  | X |  |
| Activity | 1322.2 Raise awareness to communities on appropriate existing funding mechanisms and opportunities |  | X | X |
| Activity | 1322.3 Support communities to access climate action funding through linkage meetings and support to develop funding applications |  | X | X |
| Output | 1323 High-level event held in project counties, with global leaders, experts and innovators to profile and promote gender responsive NbS and increase Kenyan investment in locally led NbS |  |  |  |
| Activity | 1323.1 Document knowledge and prepare materials for sharing/discussion |  | X | X |
| Activity | 1323.2 Hold high-level national learning and sharing event |  |  | X |

|  |  | W1 | W2 | W3 |
| --- | --- | --- | --- | --- |
| Immediate Outcome | 1330 Increased ability of WRO and YLOs to undertake evidenced-based advocacy for gender responsive and inclusive climate adaptation and resilience |  |  |  |
| Output | 1331 Evidence on benefits of gender responsive and inclusive climate adaptation and resilience generated through the project's M&E systems and specialized research |  |  |  |
| Activity | 1331.1 Conduct Baseline, GBA+ (including referral services) and endline evaluation studies | X | X | X |
| Activity | 1331.2 Conduct rapid biodiversity and gendered climate risk assessment of target implementation areas | X |  |  |
| Activity | 1331.3 Set up project Management Information System (MIS) | X |  |  |
| Activity | 1331.4 Research business case for payment for ecosystem services |  | X | X |
| Activity | 1331.5 Conduct specialized research on the social, economic, climate and biodiversity benefits of Nature Based Solutions |  | X | X |
| Output | 1332 Evidence on benefits of gender responsive and inclusive climate adaptation and resilience disseminated to communities, governments, research and academic institution |  |  |  |
| Activity | 1332.1 Develop knowledge management and dissemination strategy | X |  |  |
| Activity | 1332.2 Edit and print material as per audiences targeted in knowledge management strategy | X |  |  |
| Activity | 1332.3 Distribute material to targeted audiences | X |  | X |
| Activity | 1332.4 Organize information sharing events on evidence benefits of NbS with targeted audiences | X | X | X |
| Output | 1333 Members of WRO and YLOs trained on leadership, gender and climate change, and evidenced-based advocacy |  |  |  |
| Activity | 1333.1 Conduct mapping of WRO and YLOs in the targeted area |  |  |  |
| Activity | 1333.2 Conduct capacity needs assessment of WROs and YLOs |  |  |  |
| Activity | 1333.3 Develop training package for WROs and YLOs on leadership, gender and climate change, and evidenced-based advocacy | X |  |  |
| Activity | 1333.4 Deliver ToT on leadership, gender and climate change, and evidenced-based advocacy | X |  |  |
| Activity | 1333.5 Train WRO and YLO members on leadership, gender and climate change, and evidenced-based advocacy | X |  | X refresher |
| Activity | 1333.6 Organize information sharing events on evidence benefits of NbS with WROs and YLOs |  | X | X |
| Output | 1334 WRO and YLOs' evidenced-based advocacy plans supported to increase action on gender responsive and inclusive climate adaptation and resilience |  |  |  |
| Activity | 1334.1 Support WROs and YLOs on the development of evidenced-based advocacy plans | X |  |  |
| Activity | 1334.2 Provide inputs to WROs and YLOs for the implementation of their evidence- based advocacy plans |  | X |  |
| Activity | 1334.3 Provide supportive supervision to WROs and YLOs during the implementation of their evidence-based advocacy plans |  | X | X |