## MERL Year 3 Workplan
Objective | Activity | Deliverable | Indicator | Timeline | Responsible | Progress Update
1. Quality Delivery of MERL Functions | Maintain and implement COSME M&E framework, Theory of Change alignment, and MIS | Updated MERL framework & MIS | ≥90% MERL deliverables on time | Monthly | MERL Officer
1. Quality Delivery of MERL Functions | Conduct routine data collection, entry, and verification | Monthly monitoring datasets | 100% of data quality issues resolved within 2 weeks | Monthly | MERL Officer, Project staff
1. Quality Delivery of MERL Functions | Produce MERL reports (monthly, quarterly, annual) | Progress reports | 100% reports on time, complete, satisfactory | Monthly/Quarterly/Annual | MERL Officer
1. Quality Delivery of MERL Functions | Maintain MERL risk tracking and mitigation plans | Updated MERL risk log | 100% MERL risks tracked quarterly | Quarterly | MERL Officer + Project Manager
2. Managing Project Results & Partner Accountability | Coordinate routine monitoring with staff, WROs, YLOs | Monitoring schedules & reports | ≥90% indicators on track | Monthly | MERL Officer + Partners
2. Managing Project Results & Partner Accountability | Conduct performance/results review sessions | Review meeting minutes & action points | ≥1 review session quarterly | Quarterly | MERL Officer
2. Managing Project Results & Partner Accountability | Update project results on SAP/PMERL | Updated SAP/PMERL entries | 100% results updated | Monthly/Quarterly | MERL Officer
2. Managing Project Results & Partner Accountability | Implement partner MERL capacity strengthening follow-up plans | Training follow-up reports | 100% plans implemented | Semi-annual | MERL Officer + Partners
2. Managing Project Results & Partner Accountability | Facilitate evidence-based adaptations | Adaptation briefs | ≥2 adaptations made annually | Annual | MERL Officer + Project Manager
3. Learning, Knowledge Management & Influencing | Produce and disseminate learning products (case studies, stories, lessons) | ≥3 learning products | ≥3 learning products disseminated | Bi-annual/Annual | MERL Officer + Comms
3. Learning, Knowledge Management & Influencing | Share evidence products with external forums | ≥2 evidence briefs | ≥2 shared externally | Annual | MERL Officer + Project Manager
3. Learning, Knowledge Management & Influencing | Document best practices & lessons learned | Lessons learned report | 100% fed into project design | Quarterly | MERL Officer + Partners
3. Learning, Knowledge Management & Influencing | Maintain interactive dashboards & GIS system | Functional dashboards & GIS | System updated quarterly | Quarterly | MERL Officer
4. Capacity Strengthening of Staff, WROs, YLOs | Conduct MERL training & coaching sessions | Training reports | ≥2 capacity sessions conducted | Semi-annual | MERL Officer
4. Capacity Strengthening of Staff, WROs, YLOs | Provide ongoing coaching & mentorship | Mentorship logs | ≥80% participants show improved skills | Ongoing | MERL Officer
4. Capacity Strengthening of Staff, WROs, YLOs | Track and address MERL support needs | Support follow-up reports | 100% needs addressed | Quarterly | MERL Officer
5. Safeguarding & GEI Integration in MERL | Induct staff, WROs, YLOs, and RAs on Safeguarding & GEI | Induction reports | 100% inducted | Continuos | MERL Officer + Safeguarding Focal Point
5. Safeguarding & GEI Integration in MERL | Integrate GEI & safeguarding in all MERL tools/reports | GEI-integrated tools/reports | 100% tools updated | Ongoing | MERL Officer
5. Safeguarding & GEI Integration in MERL | Conduct quarterly GEI & safeguarding compliance checks | Compliance reports | 4 reports annually | Quarterly | MERL Officer
5. Safeguarding & GEI Integration in MERL | Ensure sex, age, disability disaggregated data (SADD) | Disaggregated datasets | 100% datasets disaggregated | Ongoing | MERL Officer

## Dashboard
Row Labels | Count of Key Activities
(blank) | 20
Grand Total | 20
Key Activities status by objective | Column Labels
| (blank) | Grand Total
1. Quality Delivery of MERL Functions | 4 | 4
2. Managing Project Results & Partner Accountability | 5 | 5
3. Learning, Knowledge Management & Influencing | 4 | 4
4. Capacity Strengthening of Staff, WROs, YLOs | 3 | 3
5. Safeguarding & GEI Integration in MERL | 4 | 4
Grand Total | 20 | 20