## Seaweed
SEAWEED
Strategic Issues identified
1 | market linakges
2 | stregnthening Association/ coops
3 | aggregation
4 | capacity/training gaps
5 | inputs
6 | value addition
7 | accredition
8 | innovations roll out and sustainavility
A | Implementation Strategy: | Training/capacity gaps
Activities |  |  |  | Resources Required | Technical Notes
1 | ID gaps - increase focus on markets/business skills |  |  | - trainers ; mentors ; peer-to-peer farming ; find champions (high producers); Victor to develop programme for model farm development | - Look at who is doing the training; not technical trainers ; - need to kickstart from reciept of seeds on the supportive supervision - key on individual monitoring
2 | train around ID'd gaps
3 | regular supportive supervision
4 | Develop a Model farm (for replication) programme to showcase economies of scale (Victor)
5 | Visit Mawimbi farms in Lamu
6
7
8
9
10
B | Implementation Strategy: | stregnthening groups/associations/coops
Activities |  |  |  | Resources Required | Technical Notes
1 | Formalize seaweed association - work within BMU structure? |  |  | meeting with Benson & Dept at KeFS responsible for setting up coops within BMUs | linked with county and ministry leadership; high value assets handed over association with oversight from govt work with dept that creates coops within BMUs
2 | regular supportive supervision and mentorship via champions (high producers)
3
4
5
6
7
8
9
10
C | Implementation Strategy: | market linakges
Activities |  |  |  | Resources Required | Technical Notes
1 | For offtake: quality and quantity of seaweed - focus on spinosium (cottonii brings higher price but susceptible to disease) |  | i | 1. QA check 2. | Shimoni port has opened up opportunity to export directly to buyer rather than going thru TZA - Punching needles - to confirm moisture content - Kenya Plant Health Inspectorate/ KMFRI on ,certification of composition of seaweed
2 | Ideally comes to offtaker aggreggated, dried, sorted, QA'd, pressed and bailed; need 88metric tons for container; want to ship every 3 months (240metric tons per year)
3 | Animal & fish feeds: Uganda, Rwanada Buruni and DRC; trials taking place now
4 | Organic fertilizer & biostimulants: local market
5 | Energy meal bars/biscuit: UNHCR
6 | Extraction for carageenan in Kenya
7
8
9
10
D | Implementation Strategy: | enhance production
Activities |  |  |  | Resources Required | Technical Notes
1 | Bring in labour (youth) for farm set up and harvest |  |  | Boats? Matatu? agree on management of the boats- prioritise seaweed and keen on attitude/thinking on commercial- have SMC present the boats ? | Provide collective transport to farmers who may not live close to the farm site ; KeFS can co-manage boats with Plan ; tracing and QC important re. Base Titanium example
2 | ID suitable sites for farm expansion and new farmers/groups ; find sites suitable for commercial harvesting
3 | Transport: Facilitate access to farms with better sites (boats) during planting & harvest
4 | regular supportive supervision and mentorship via champions (high producers)
5 | provide incentives for higher production? (drag boats, higher prices, youth labourers, )
6 | raft boats to move to the harvest shore
7 | build trust and transparancy and quality control - digital/hardcopy tracking/tracing app/system? Pilot an app with strong groups
8 | in interim as the coswain training is ongoing engage coxswain from KeFS or County Goverment to support farmers
9
10 | provide bailers and bail bags
E. | Implementation Strategy: | Aggreggation
Activities |  |  |  | Resources Required | Technical Notes
1 | select high producing groups with best management practices |  |  | KWFI (WRO) currently working on cleaning and QC aggregation via service agreements;
2 | move to drying sheds
3 | KWFI (WRO) contracted for cleaning and QA/QC;
4
5 | manual portable bailer
6 | Bring to warehouse that has pest contol
7 | Kenya health plant must inspect before export (there is one in Shimoni)
8
9
10

## Forestry-Mangrove
FORESTRY
Strategic Issues identified
1 | Illegal Harvesting
2 | Grazing
3 | Sedimentation- smoothering the saplings and trees in the tidal flats
4 | Plastic pollution
5
6
7
8
A | Implementation Strategy: | Promote regeneration of mangrove forest
Activities |  |  | Resources Required | Technical Notes
1 | 1. Protection-Recruitment of scouts through the user rights for prevention of illegal cutting. planting on affected areas. Foundational training at KFS station -3 weeks paralegal training in Londiani-Kenya forestry college. |  | Shovels for use during planting, facilitators during trainings, Jembes for opening up channels, Mandays- labour
2 | Enrichment planting on identifies areas
4 | Awareness creation to senzitze community on alternative sources of wood material
5 | Hydrological modification on identified areas- to enhance natural regeneration/create suitable conditions for planting
6
7
8
9
10
B | Implementation Strategy: | Pomote alternative sources of fodder
Activities |  |  | Resources Required | Technical Notes
1 | 1.provision of fodder seeds for farmers |  | Facilitators, fodder propagation materials
2 | 2. sensitization meeting with farmers on the issue of protection- cocreate with the community on alternative . grazing options.
3 | Planting of fodder baffers along the edges-riparian lands
4
5
6
7
8
9
10
C | Implementation Strategy: | Manage Soil erosion in the hinterland facing tidal flats
Activities |  |  | Resources Required | Technical Notes
1 | Planting of bamboo (Pilot) to prevent sedimentation |  | Mandays, grass and bamboo propagation materials, spades, Jembe | Field assessment on hydrological modification on the targeted areas.
2 | Planting grass as advised on which species to plant by KALRO-Vertiver grass- prevent sedimentation and provide grazing fields (this would serve both as deterent for siltation in mangroves and grazing material for cattle
3
4
5
6
7
8
9
10
D | Implementation Strategy: | Solid waste management
Activities |  |  | Resources Required | Technical Notes
1 | Awareness Creation
2 | Link community groups to major waste recycling companies
3 | Organise ocassional cleaup days
4
5
6
7
8
9
10
E. | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10

## Forestry-Terretrial
FORESTRY
Strategic Issues identified
1 | Illegal harvesting
2 | Grazing
3 | pollution- plastic bag waste and general waste
4
5
6
7
8
A | Implementation Strategy: | Promote regeneration of mangrove forest
Activities |  |  | Resources Required | Technical Notes
1 | Protection for natural regeneration- 1. recruitment of scouts through the user rights for prevention of illegal cutting. planting on affected areas. Foundational training at KFS station -3 weeks paralegal training in Londiani-Kenya forestry college. |  | Cook stoves, Scouts, workshop venues, other conference facilities,
2 | Distribution of energy saving jikos
3 | Create a platform for information sharing between the youth and community elders- this will help tackle the issue on erosion of indigenous and traditional ecological knowledge (1) workshop/forums towards coming up with Kaya youth champions
4
5
6
7
8
9
10
B | Implementation Strategy: | Promote alternative sources of fodder
Activities |  |  | Resources Required | Technical Notes
1 | 1.provision of fodder for alternative grazing lands. |  | Facilitators, fodder propagation materials
2 | 2. sensitization meeting with farmers on the issue of protection- cocreate with the community on alternative . grazing options.
3 | Planting of fodder baffers along the edges-buffer zones, planting trees for boundary alignment
4
5
6
7
8
9
10
C | Implementation Strategy: | Solid waste management
Activities |  |  | Resources Required | Technical Notes
1 | Sensistization through the CFAs on waste managements |  | Mandays, grass and bamboo propagation materials, spades, Jembe
2 | Organise ocassional cleaup days-Chonyi and Gonja forest
3
4
5
6
7
8
9
10
D | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10
E. | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10

## EBA + GJJ
EBA
Strategic Issues identified
1 | Dis-jointed EBAs and there's need for a more coordinated/joint strategic level EBA action plan by WROs and YLOs |  |  | Points for Consideration
2 | There's need for a link between the project's strategic issues and the EBAs - GRAPP and HHAP- need a set of activities to integrate these three components |  |  | Joint presentation at County level Working Groups that include other organizations
3 | Identification and adoption of advocacy level actions from the GJJ Groups HHAP (integrate these into the EBAs/ joint advocacy plans) |  |  | In an effort to ensure that the WROs and YLOs all support each other and the selected groups in implementing their EBAs, with the selected being the leads, identify any cross cutting advocacy asks from the EBA and advance these together, complementing strategies/ approaches for better results
4
5 |  |  |  | EBAs for YLOs and WROs to be aligned to both GRAPPs and Community Level HHAP
6 |  |  |  | Push for funding (from COSME) for the common/ joint advocacy asks identified by all WROs and YLOs
7
8
A | Implementation Strategy: | Coordinated and Joint Advocacy by WROs and YLOs -Sustainability action on movement building
Activities |  |  | Resources Required |  | Technical Notes
1 | Convene a meeting for all 13 WROs and YLOs in April/May 2026 to identify joint advocacy asks and develop detailed strategic plans and roadmaps to have these implemented (resources required -human + financial, evidence required, timeframes, partnerships with other actors and government representatives, thematic focus areas for the advocacy +roles and responsibilities)including validation of existing data- this to happen after full alignment to GRAPP and Community Level HHAP |  | 1. Policy briefs need to be developed and shared with all the members of WROs and YLOs who have been trained in EBA to take these forward 2. Leverage the WROs and YLOs members trained in EBA |  | 1. Contextual groups to be supported to develop memoranda (issues identified + policy asks) for the presentation to county during the Annual Development Planning (ADP) 2. Conduct consultations with the community to jointly identify areas of concern to further strengthening advocacy asks to be advanced by WROs and YLOs (Having EBAs) 3. Strengthened partnerships with other actors working with WROs and YLOs beyond COSME 4. Policy Briefs have demonstrated potentiality to work- develop these backed by data from community consultations 5. Collection of evidence to back up policy asks (developing policy briefs to guide such processes) 6. Potential leverage of sponsorship funds in advocacy efforts in sponsorship locations/ targeting sponsorship communities
2 | Map existing funding mechanisms and opportunities (at this joint meeting) which WROs and YLOs can tap into (including how to access this funding (development of funding proposals), support needed from Plan to access)
3 | More immediate activity: Organize two joint meetings (for Kwale and Kilifi WROs and YLOs jointly), identify how other WROs and YLOs will work with and support the selected organizations in the remaining project duration to implement and advance their EBAs. How the EBA strategies will be jointly implemented in this duration, modalities of implementation etc
4
5
6
7
8
9
10
B | Implementation Strategy: | Validation of GRAPP issues + Joint EBA strategies developed with communities
Activities |  |  | Resources Required |  | Technical Notes
1 | Validation meetings in each ward for the GRAPPs (including the issues they identified) with the communities (led by WROs and YLOs), with draft memoranda developed identifying actions to be taken up by the different actors (the community-chiefs, BMUs, the CSOs and CBOs and government) -this includes priority actions and timelines |  |  |  | 1. During the community meeting, present issues identified from GRAPP, then proceed with validation and adoption with the community 2. Leveraging the existing information from the GRAPP Data collection process 3. Leverage the political goodwill that's currently available at counties to advance specific advocacy asks 4. During community sensitization meetings, present on the identified funding mechanisms from the GRAPP
2 | WRos and YLOs to convene meetings in each ward for sensitizing the community on existing funding mechanisms and opportunities which they can tap into and map support needed
3 | Organize linkage meetings to support communities to develop funding applications to access the identified climate action funds
4 | Session with WROs and YLOs to identify alignment of their EBAs with GRAPPs
5
6
7
8
9
10
C | Implementation Strategy: | Identify and adopt advocacy issues from the GJJ Community Level HHAP to be supported by the WROs and YLOs in advancing these either as part of EBA or the strategic level advocacy plans
Activities |  |  | Resources Required |  | Technical Notes
1 | Organize a two day workshop/ training to take the YLOs and WROs through a refresher/ summary of the GJJ model + manual to further inform their participation in HHAP sessions
2 | WROs and YLOs to attend community HHAP sessions, identifying advocacy asks/opportunities to be included in their advocacy plans
3 | Review the already prepared EBAs + joint strategic level advocacy priorities integrating and aligning with the community level action plans identified
4 | Assign WROs and YLOs to specific GJJ Clusters based on their locations
5 | Develop a monitoring tool to track the WRO and YLO engagement with the GJJ clusters (topics discussed, advocacy asks identified, milestones tracked)
6
7
8
9
10
D | Implementation Strategy: | Supportive supervision of EBA implementation
Activities |  |  | Resources Required |  | Technical Notes
1 | Develop a advocacy directory/ dashboard to track agreed upon advocacy asks (track progress, bottlenecks, any pivoting required etc)
2
3
4
5
6
7
8
9
10
GRAPP
Strategic Issues identified
1 | WROs and YLOs EBAs not aligned to the GRAPPs
2
3
4
5
6
7
8
A | Implementation Strategy:
Activities |  |  | Resources Required |  | Technical Notes
1
2
3
4
5
6
7
8
9
10
B | Implementation Strategy:
Activities |  |  | Resources Required |  | Technical Notes
1
2
3
4
5
6
7
8
9
10
C | Implementation Strategy:
Activities |  |  | Resources Required |  | Technical Notes
1
2
3
4
5
6
7
8
9
10
D | Implementation Strategy:
Activities |  |  | Resources Required |  | Technical Notes
1
2
3
4
5
6
7
8
9
10
HOUSEHOLD ACTION PLANS
Strategic Issues identified |  |  |  | points for consideration
1 | Sustained tracking, monitoring, supervision and evaluation of the implementation of the HHAP (including capturing the learnings) beyond the project duration |  |  | Identification of model households for learnings
2 |  |  |  | GJJ focal point person from each group
3
4
5
6
7
8
A | Implementation Strategy: | Working with WROs and YLOs in supervision, monitoring and evaluation of the HHAP
Activities |  |  | Resources Required |  | Technical Notes
1 | Two day workshop with YLOs and WROs (conduct refresher trainings on GJJ) to help facilitate their effective participation and support for the HHAP process
2 | WROs and YLOs to attend Community HHAP sessions (interact with the action plans, identify advocacy opportunities, and identify potential support areas to the community in implementing their action plans)
3 | Develop a joint monitoring tool to be utilized by WROs and YLOs (input progress updates during each visit, support areas identified, milestones progress from HHAP)
4
5
6
7
8
9
10
B | Implementation Strategy: | Identify model households for peer-to-peer learnings among the GJJ clusters
Activities |  |  | Resources Required |  | Technical Notes
1 | Develop a selection criteria for the identification of what qualifies as a 'model household'. This criteria to be jointly developed with the community
2 | Identify the model households to be engaged in the peer-to-peer learning process
3 | Identification of GJJ focal point persons/ champions from the trained groups
4 | Link the focal point persons to WROs and YLOs and other community structures for support in convening relevant reflection meetings to further review progres of the HHAP
5 | Roll out and implementation of the HHAP monitoring framework (to track milestones during the HHAP implementation)
6 | Capacity building of the WROs and YLOs on the HHAP monitoring framework for joint implementation with PIK
7
8
9
10
C | Implementation Strategy:
Activities |  |  | Resources Required |  | Technical Notes
1
2
3
4
5
6
7
8
9
10
D | Implementation Strategy:
Activities |  |  | Resources Required |  | Technical Notes
1
2
3
4
5
6
7
8
9
10

## VSLA-REGAG - Schools
SCHOOLS
Strategic Issues identified
1 | Unsupportive environment in schools by the BOM and HOI
2 | stakeholders lack awareness of the 4k clubs projects in schools
3 | new patrons and matrons lack the knowledge of the revised 4-K- club training guide
4 | inadequate technical support to implement climate change initiatives in schools
5 | Getting the MoE to suport 4K-club projects
6
7
8
A | Implementation Strategy: | SENSITIZATION MEETINGS
Activities |  |  | Resources Required | Technical Notes
1 | Organize a sensization meeting for all the key stakeholders on ward level i.e chiefs , ministry of agriculture, environment , NEMA , water |  | Project support - Reimbursements (Transport, lunches)
2 | Refresher trainings to the matron and patrons , to equip them on the training guide
3 | Courtesy visit for Ministry of Agricuoture & MoE to streamline stakeholder support
4
5
6
7
8
9
10
B | Implementation Strategy: | Continued technical support through the County Departments for Agriculture
Activities |  |  | Resources Required | Technical Notes
1 | Develop an agreed technical support & monitoring plan
2 | Support technical officers to visit schools at least 2 times per term for followup visits
3
4
5
6
7
8
9
10
C | Implementation Strategy: | Exchange sharing forums to share best practices especially for Roots & Shoots
Activities |  |  | Resources Required | Technical Notes
1 | Cluster schools as per matrons/patrons who participated in the R&S exchange visit
2 | Ecourage 4K clubs to register for the PAS competition
3 | Idenfy role model schools for exchange learning visits
4
5
6
7
8
9
10
D | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10
REGENERATIVE AGRO
Strategic Issues identified
1 | Weak link by county depertment of agriculture to support continous operation of demos
2 | Retrogressive gender & cultural practices marginalizing women in Agriculture- land tenure
3 | Uncordinated implementation of demo plots - each demo plot doing its own things
4 | Slow uptake of technical knowledge and skills- - pest & Disease infestation
5 | water shortage/low water pressure in tanks
6
7
8
A | Implementation Strategy: | Continued mentorship support by technical officers to demo plots
Activities |  |  | Resources Required | Technical Notes
1 | Planning meeting with County technical officers |  | One day confrence review & Planning meeting, 2 round reimbursements (Tranport & Lunch)
2 | Suport regular visists to the regenerative groups by the county technical staff
3
4
5
6
7
8
9
10
B | Implementation Strategy: | Hold a county level stakeholder forum to share requirements for sustaining the demo plots
Activities |  |  | Resources Required | Technical Notes
1 | Map regenerative Agric stakeholders |  | Transport for stakeholders, 2-day confrence for stakeholders
2 | Identify demo specific issues for sustainability in each of the sites
3 | Jointly identify support areas and share with stakeholders for continued support
4 | Doing institutional linkages - Sunculture (Pumps), FLLoCA, GJJ (Gender transformative, land tenure and cultural engagement action on regenerative agriculture)
5
6
7
8
9
10
C | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10
D | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10
VSLA
Strategic Issues identified
1 | CBT taking ownership of the refresher training to group members
2 | Unclear method to sustain the expertisee support to VSLAs - sustainable way to wean out the ToTs
3 | Trust building amongst CBTs and group membees including leaders
4 | Conflict and mistrust amongst VSLA/Group members
5 | Weak documentation and data recording - appreciate successes
6 | inadequate access for credit for growth and more support to members
7 | Low growth and transition opportunities by VSLAs - access to tenders especially
8
A | Implementation Strategy: | Support the CBTs to continue offering the expertisee support
Activities |  |  | Resources Required | Technical Notes
1 | Re-assess the capacity of the CBTs through an assessment
2 | Re-create a refresher to ensure CBTs get capacity to continue supporting the CBTs
3
4
5
6
7
8
9
10
B | Implementation Strategy: | Linkages with external finance and support orgnizations for other services
Activities |  |  | Resources Required | Technical Notes
1 | Linkages to other services that will bring coesion
2
3
4
5
6
7
8
9
10
C | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10
D | Implementation Strategy:
Activities |  |  | Resources Required | Technical Notes
1
2
3
4
5
6
7
8
9
10