## Sheet1
COSME Workplan & Reporting Workback Schedule
Y4 AWP | 2026-01-01 | 2026-02-01 | [27 empty] | 2026-03-01 | [30 empty] | 2026-04-01 | [29 empty] | 2026-05-01
Workplan Narrative |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CNO shares workplan templates
AWP workshop | bar: 2026-03-01 9 to 2026-03-01 13
PIK drafts workplan | bar: 2026-03-01 16 to 2026-03-01 19; 2026-03-01 23 to 2026-03-01 27
PIK submits draft #1 to CNO | bar: 2026-03-01 27
CNO reviews draft #1 | bar: 2026-03-01 27; 2026-03-01 30 to 2026-04-01 2
CNO to submit feedback to PIK | bar: 2026-04-01 2
PIK reviews feedback and revises workplan | bar: 2026-04-01 7 to 2026-04-01 10; 2026-04-01 13
PIK submits draft #2 to CNO | bar: 2026-04-01 13
CNO reviews draft #2 | bar: 2026-04-01 14 to 2026-04-01 17; 2026-04-01 20
CNO to submit feedback to PIK | bar: 2026-04-01 20
PIK reviews feedback and revises workplan | bar: 2026-04-01 21 to 2026-04-01 24; 2026-04-01 27
PIK submits draft #3 to CNO | bar: 2026-04-01 27
CO Leadership Review | bar: 2026-04-01 28 to 2026-04-01 30; 2026-05-01 4 to 2026-05-01 5
CNO final review/edit/format | bar: 2026-05-01 6 to 2026-05-01 8; 2026-05-01 11 to 2026-05-01 13
Review and sign off by CNO SPM | bar: 2026-05-01 11 to 2026-05-01 13
Submit to GAC | bar: 2026-05-01 15
Partner Workplans |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CNO receives Cascadia draft #1 workplan | bar: 14
CNO reviews Cascadia draft #1 workplan | bar: 15 to 17
CNO shares feedback/questions with Cascadia, if needed | bar: 17
Cascadia revises workplan and submits draft #2, if needed | bar: 20 to 21
CNO reviews Cascadia draft #2, if needed | bar: 22 to 23
Integration of Cascadia workplan into Plan workplan | bar: 29 to 30
CNO receives JGI draft #1 workplan | bar: 7
CNO reviews JGI draft #1 workplan | bar: 8 to 10
CNO shares feedback/questions with JGI, if needed | bar: 10
JGI revises workplan and submits draft #2, if needed | bar: 13 to 15
CNO reviews JGI draft #2, if needed | bar: 16 to 17; 20
Integration of JGI workplan into Plan workplan | bar: 21 to 22
Budget |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CNO shares budget template (KCO, Cascadia, JGI) | bar: 2
Partners reach out to CNO for any clarification on the template | bar: 2 to 6
Annual Work Plan Worshop | bar: 9 to 13
PIK completes draft #1 budget | bar: 16 to 19; 23 to 27
PIK submits draft #1 to CNO | bar: 27
CNO reviews draft #1 | bar: 30 to 2
CNO to submit feedback to PIK | bar: 2
PIK reviews feedback and revises budget | bar: 7 to 10; 13
PIK submits draft #2 to CNO ¦ JGI & Cascadia submit their Y3 AWP budget | bar: 13
CNO reviews all budgets & reaches out for any clarification | bar: 13 to 17; 20 to 21
CNO finalizes and consolidates all budgets | bar: 22 to 24; 27 to 30
CM share budget SCM & SPM/PM | bar: 4
SCM & SPM reviews budget | bar: 4 to 8
CNO Director review | bar: 11 to 15
Submit to GAC | bar: 15
Y3 AR | 2026-01-01 | 1: 2026-02-01; 1: 2026-03-01; 1: 2026-04-01; 1: 2026-05-01
Narrative Report |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CNO share narrative report templates
PIK drafts report | bar: 2026-02-01 16 to 2026-02-01 20; 2026-02-01 23 to 2026-02-01 27; 2026-03-01 2 to 2026-03-01 6; 2026-03-01 9 to 2026-03-01 13; 2026-03-01 16 to 2026-03-01 19; 2026-03-01 23 to 2026-03-01 27; 2026-03-01 30 to 2026-04-01 1
PIK submits draft #1 to CNO | bar: 2026-04-01 1
CNO reviews draft #1 | bar: 2026-04-01 2; 2026-04-01 7 to 2026-04-01 10; 2026-04-01 13 to 2026-04-01 17
CNO to submit feedback to PIK | bar: 2026-04-01 17
PIK reviews feedback and revises report | bar: 2026-04-01 20 to 2026-04-01 24; 2026-04-01 27 to 2026-04-01 30
PIK submits draft #2 to CNO | bar: 2026-05-01 4
CNO reviews draft #2 | bar: 2026-05-01 5 to 2026-05-01 8
Joint call PIK & CNO to review outstanding questions/comments (if needed) | bar: 2026-05-01 11
CNO finalizes draft report for submission to GAC | bar: 2026-05-01 12 to 2026-05-01 15
CNO submits draft report to GAC | bar: 2026-05-01 15
CO Leadership Review | bar: 2026-05-01 18 to 2026-05-01 22
CNO final review/edit/format | bar: 2026-05-01 25 to 2026-05-01 28
Review and sign off by CNO SPM | bar: 2026-05-01 27 to 2026-05-01 28
Submit to GAC | bar: 2026-05-01 29
Partner Narrative Reports |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CNO receives Cascadia draft #1 report | bar: 30 to 1
CNO reviews Cascadia draft #1 report | bar: 4 to 7
CNO shares feedback/questions with Cascadia, if needed | bar: 7
Cascadia revises report and submits draft #2, if needed | bar: 8
CNO reviews Cascadia draft #2, if needed | bar: 11 to 12
Integration of Cascadia report into Plan report | bar: 13 to 14
CNO receives JGI draft #1 report | bar: 30 to 1
CNO reviews JGI draft #1 report | bar: 4 to 7
CNO shares feedback/questions with JGI, if needed | bar: 6 to 7
JGI revises report and submits draft #2, if needed | bar: 8; 11
CNO reviews JGI draft #2, if needed | bar: 11 to 12
Integration of JGI report into Plan report | bar: 13 to 14
Financial Report |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
CNO shares financial report template (KCO, JGI, & Cascadia | bar: 6 to 7
PIK completes draft #1 financial report | bar: 8 to 10; 13 to 17; 20 to 24
PIK submits draft #1 to CNO | bar: 25
Cascadia submits financial report to CNO | bar: 30 to 1
JGI submits financial report to CNO | bar: 10
CNO reviews draft #1 | bar: 27 to 1; 4 to 8
CNO to submit feedback to PIK | bar: 8
PIK reviews feedback and revises financial report | bar: 11 to 15
PIK submits draft #2 to CNO | bar: 15
CM reviews and consolidates all financial reports for further review. | bar: 18 to 22
CM submits report to SCM and SPM/PM reivew | bar: 22
SCM & SPM/PM review completed and ready for director review | bar: 22; 25 to 26
Director reivew | bar: 27 to 28
Submit to GAC | bar: 29
Legend
Weekend
Holiday
Important Due Dates
Holidays in Kenya
Mar 19-20: Likely Eid al-Fitr
April 3: Good Friday
April 6: Easter Monday
May 1: Labour Day
Holidays in Canada
Feb 16: Family Day
April 3: Good Friday
April 6: Easter Monday
May 18: Victoria Day
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per their agreements, partners are not required to complete a workplan and are instead expected to collaborate with Plan and partners to develop AWPs. We will request that each partner does complete a workplan for their relevant activities - keeping the template as light as possible
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be discussed with each partner when they think they could submit a workplan - if earlier than PIK's 1st draft deadline to CNO, that would be ideal